## Status
Class Status
Instructions: | For your first assignment you will need to fill out A0_Plan Each week you will fill out the corresponding Ax_Status tab along with your Team Status. Note the gray fields are the field you need to change. All other fields are formulas that will populate back to this page's status. Submit a copy of this file, updated each week.
| Tasking | Percent Complete | Totals |  | Milestones | Done
| Planned/Scheduled | 97.44% | 0 |  | Basic Certification | 80%
| Story Points Assigned | 0% | 0 |  | Portfolio | 100%
| Completed Tasks | 87.18% | 0 |  | Silver Certification | 60%
[5 empty] | Job Search | 100%
[5 empty] | Professional Development | 100%
| Personal | Velocity | Hrs/Task | Avg Hrs/Task | Team Member | 1 | 2 | 3 | 4 | 5
| Week 01 | 0 | 3 | 0.5 | Week 01 | 0 | 0 | 0 | 0 | 0
| Week 02 | 0 | 4 | 0.66667 | Week 02 | 0 | 0 | 0 | 0 | 0
| Week 03 | 0 | 4.5 | 0.75 | Week 03 | 0 | 0 | 0 | 0 | 0
| Week 04 | 0 | 5.5 | 0.91667 | Week 04 | 0 | 0 | 0 | 0 | 0
| Week 05 | 0 | 14 | 2.3333 | Week 05 | 0 | 0 | 0 | 0 | 0
| Week 06 | 0 | 4.5 | 0.75 | Week 06 | 0 | 0 | 0 | 0 | 0
| Week 07 | 0 | 1 | 0.16667 | Week 07 | 0 | 0 | 0 | 0 | 0

## Team Status
Team member tasking
Completed Tasks
| Day |  | Team member 1 | Team Member 2 | Team Member 3 | Team Member 4
Assignment 1
| 1 | 1
| 1 | 2
| 1 | 3
| 2 | 1
| 2 | 2
| 2 | 3
Velocity
Assignment 2
| 3 | 1
| 3 | 2
| 3 | 3
| 4 | 1
| 4 | 2
| 4 | 3
Velocity
Assignment 3
| 5 | 1
| 5 | 2
| 5 | 3
| 6 | 1
| 6 | 2
| 6 | 3
Velocity
Assignment 4
| 7 | 1
| 7 | 2
| 7 | 3
| 8 | 1
| 8 | 2
| 8 | 3
Velocity
Assignment 5
| 9 | 1
| 9 | 2
| 9 | 3
| 10 | 1
| 10 | 2
| 10 | 3
Velocity
Assignment 6
| 11 | 1
| 11 | 2
| 11 | 3
| 12 | 1
| 12 | 2
| 12 | 3
Velocity
Assignment 7
| 13 | 1
| 13 | 2
| 13 | 3
| 14 | 1
| 14 | 2
| 14 | 3
Velocity

## Backlog
BackLog
Count | Ref | Issues | Hidden Colum - create a orginal menu list | Hidden Column - menu list that removes items as selected |  | Hidden status
[5 empty] | 97.44% | 87.18%
0 | PP1 | Planning Schedule | 0_PP1_Planning Schedule |  | 1 | 1 | Completed
0 | B0 | Basic Certification |  |  |  |  | 80%
1 | B1 | Scheduled Basic Meeting with Career Services | 1_B1_Scheduled Basic Meeting with Career Services |  | 1 | 1
2 | B2 | Create Professional Online Profiles | 2_B2_Create Professional Online Profiles |  | 1 | 1
3 | B3 | Informational Interview Overview | 3_B3_Informational Interview Overview |  | 1 | 1
4 | B4 | Interviewing: VMOCK | 4_B4_Interviewing: VMOCK |  | 1 | 1
5 | B5 | Elevator Pitch: 5 Sentences | 5_B5_Elevator Pitch: 5 Sentences |  | 1
0 | S0 | Silver Certification |  |  |  |  | 60%
6 | S1 | Scheduled Silver Meeting with Career Services | 6_S1_Scheduled Silver Meeting with Career Services |  | 1
7 | S2 | Completed 100% LinkedIn Profile | 7_S2_Completed 100% LinkedIn Profile |  | 1
8 | S3 | Completed 100% BYUI Connect Profile | 8_S3_Completed 100% BYUI Connect Profile |  | 1
9 | S4 | Completed 100% Handshake Profile | 9_S4_Completed 100% Handshake Profile |  | 1
10 | S5 | Resume in Green Zone on VMOCK | 10_S5_Resume in Green Zone on VMOCK |  | 1 | 1
11 | S6 | Informational Interview 1 | 11_S6_Informational Interview 1 |  | 1 | 1
12 | S7 | Informational Interview 2 | 12_S7_Informational Interview 2 |  | 1 | 1
13 | S8 | Informational Interview 3 | 13_S8_Informational Interview 3 |  | 1 | 1
14 | S9 | Informational Interview 4 | 14_S9_Informational Interview 4 |  | 1 | 1
15 | S10 | Informational Interview 5 | 15_S10_Informational Interview 5 |  | 1 | 1
0 | P0 | Portfolio Review |  |  |  |  | 100%
16 | P1 | Photo | 16_P1_Photo |  | 1 | 1
17 | P2 | Resume | 17_P2_Resume |  | 1 | 1
18 | P3 | Cover Letter Template | 18_P3_Cover Letter Template |  | 1 | 1
19 | P4 | References | 19_P4_References |  | 1 | 1
20 | P5 | Elevator Pitch/About | 20_P5_Elevator Pitch/About |  | 1 | 1
21 | P6 | Projects | 21_P6_Projects |  | 1 | 1
0 | J0 | Job Search |  |  |  |  | 100%
22 | J1 | Networking List | 22_J1_Networking List |  | 1 | 1
23 | J2 | Network Contact List | 23_J2_Network Contact List |  | 1 | 1
24 | J3 | Company Dossiers | 24_J3_Company Dossiers |  | 1 | 1
25 | J4 | Job Application 1 | 25_J4_Job Application 1 |  | 1 | 1
26 | J5 | Job Application 2 | 26_J5_Job Application 2 |  | 1 | 1
27 | J6 | Job Application 3 | 27_J6_Job Application 3 |  | 1 | 1
28 | J7 | Job Interviewing | 28_J7_Job Interviewing | 28_J7_Job Interviewing |  | 1
0 | D0 | Professional Development |  |  |  |  | 100%
29 | D1 | Ethics in Technology | 29_D1_Ethics in Technology |  | 1 | 1
30 | D2 | Mental Health & Professional Success | 30_D2_Mental Health & Professional Success |  | 1 | 1
31 | D3 | Design Your Life: Chap 1: Health, Work, Play, & Love | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love |  | 1 | 1
32 | D4 | Design Your Life: Chap 2: Work/Life view/compass | 32_D4_Design Your Life: Chap 2: Work/Life view/compass |  | 1 | 1
33 | D5 | Design Your Life: Chap 3: Good Times Journal | 33_D5_Design Your Life: Chap 3: Good Times Journal |  | 1 | 1
34 | D6 | Design Your Life: Chap 4: Mind Map | 34_D6_Design Your Life: Chap 4: Mind Map |  | 1 | 1
35 | D7 | Design Your Life: Chap 5: Odyssey Plans | 35_D7_Design Your Life: Chap 5: Odyssey Plans |  | 1 | 1
36 | D8 | The 2-Hour Job Search: Prioritization (Chap 1-4) | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) |  | 1 | 1
37 | D9 | The 2-Hour Job Search: Outreach (Chap 5-8) | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) |  | 1 | 1
38 | D10 | The 2-Hour Job Search: Execution (Chap 9-10) | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) |  | 1 | 1
0 | A0 | Additional Tasks
39 | A1 | test1 | 39_A1_test1
40 | A2 | test 2 | 40_A2_test 2
41 | A3 | test 3 | 41_A3_test 3
42 | A4 | test 4 | 42_A4_test 4

## A0_Plan
|  |  |  | Hidden | Hidden | Hidden | Hidden | Hidden
Assign 0: Planning Schedule | [9 empty] | Story Points Chart
Instructions: | [9 empty] | Complexity | Complexity Description | CS Example Task | Class Example
1 | Read over each of the assignments in the Backlog (found in iLearn course) In the Planning Assignment column, select which task you plan on completing for each day of the semester. | [7 empty] | 1 | 1 Point | Very simple, minimal effort, well understood | Change a button's color in a web app | - Upload a photo for portfolio - Schedule a meeting with Career Services
2 | Examine the Story Point chart to the right. Mouse over and Read the comment in the Story Point column's title (below). | [7 empty] | 2 | 2 Points | Simple task, few moving parts | Add a new field to a database and update UI | - Create Networking List - Write 5-sentence Elevator Pitch
3 | Assign story points to each of the assignments, based on the complexity of the task. | [7 empty] | 3 | 3 Points | Moderate complexity; some research or testing needed | Implement login with form validation | - Complete LinkedIn or Handshake profile - Read and reflect on “Design Your Life: Chap 1–2”
4 | Verify that the Planned Velocity Chart has a even variance and trend. | [7 empty] | 5 | 5 Points | Complex; multiple steps or edge cases | Integrate third-party API (e.g., payment gateway) | - Write a resume or cover letter template - Conduct Informational Interview 1–2
[9 empty] | 8 | 8 Points | Very complex; uncertainty, multiple components | Build a basic real-time chat feature | - Resume in Green Zone on VMOCK - Conduct 4–5 Informational Interviews - Projects section for Portfolio
[9 empty] | 13 | 13 Points | Extremely complex or poorly understood | Refactor large legacy module or migrate backend | - Prepare for and perform Job Interviews - Create full Odyssey Plans (Design Your Life: Chap 5) - Apply to 3 jobs with custom materials
[9 empty] | 21 | 21+ Points | Too large – break this down | “Build entire website” — needs decomposition | - "Complete All Silver Certification Requirements" (too broad; break into subtasks)
Day |  | Planned Assignment | Story Points | Scheduled | SP Complete | Completed | Actual Hours | Linke to Artifacts
1 | 1 | 0_PP1_Planning Schedule | 0 | DAY_1 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/StudentTrackingAssignments.xlsx
1 | 2 | 17_P2_Resume | 0 | DAY_1 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/Alejo%20Alegre%20Bustos%20-%20Resume.pdf
1 | 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love |  | DAY_1 | 0 | Done | 0.5 | from my perspective, the best to do first is an introspection about our life, to see which jar is full or not in our life(health, work, play, happiness, and love). We can start working from there, after that, it depends on us, our lifestyle, and long-term goals. i think one of the best things we can do is to set priorities in these four sections and build from there.
2 | 1 | 5_B5_Elevator Pitch: 5 Sentences |  | DAY_2 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/speach-elevetaro.docx
2 | 2 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass |  | DAY_2 | 0 | Done | 0.5 | It was a great chapter, it's really great to already have a compas that govern every other aspects in my life. I think the gospel of Jesus-Christ is the best compas we can have in our life, from there we can start thinking about working and what impact we can let it have in our life.
2 | 3 | 9_S4_Completed 100% Handshake Profile |  | DAY_2 | 0 | Done | 0.5 | https://byui.joinhandshake.com/profiles/fbc2a9
|  | Assignment 1 Planned Velocity | 0
3 | 1 | 1_B1_Scheduled Basic Meeting with Career Services |  | DAY_3 | 0 | Done | 0.5 | https://app.joinhandshake.com/stu/appointments/16395626
3 | 2 | 8_S3_Completed 100% BYUI Connect Profile |  | DAY_3 | 0 | Done | 1 | https://ces.peoplegrove.com/profile/alejoalegrebustos/
3 | 3 | 33_D5_Design Your Life: Chap 3: Good Times Journal |  | DAY_3 | 0 | Done | 1 | This chapter is all about tracking your days to notice what actually gives you energy and makes you feel alive. For a few weeks, you write down what you do, how much energy you had, and how engaged you felt during each activity. The point is to catch the moments when time flies, when you’re fully into something, or when you feel drained. Once you look back at your notes, patterns start to show—things you really enjoy, the settings where you thrive, the kind of work or interactions that light you up. It’s not about what you think you “should” like, but about what your own experience is telling you.
4 | 1 | 2_B2_Create Professional Online Profiles |  | DAY_4 | 0 | Working | 0 | 0
4 | 2 | 3_B3_Informational Interview Overview |  | DAY_4 | 0 | Done | 0.5 | https://app.joinhandshake.com/stu/appointments/16395626
4 | 3 | 34_D6_Design Your Life: Chap 4: Mind Map |  | DAY_4 | 0 | Done | 1 | After you spot the paterns tought in chapter 3, the next step is to open up possibilities with a mind map. You start with a word or idea from your journal maybe something like “teaching”,“outdoors” or “design.” Put it in the center of a page and let your thoughts branch out. Write down anything that comes to mind, no matter how random. Then branch those ideas again and see where they lead. The goal is to break out of straight line thinking and discover connections or paths you wouldn’t see otherwise.
|  | Assignment 2 Planned Velocity | 0
5 | 1 | 20_P5_Elevator Pitch/About |  | DAY_5 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/speach-elevetaro.docx
5 | 2 | 14_S9_Informational Interview 4 |  | DAY_5 | 0 | Done | 0.5 | I interview a persona in a career fair that I attended on Wednesday
5 | 3 | 35_D7_Design Your Life: Chap 5: Odyssey Plans |  | DAY_5 | 0 | Done | 1.5 | I think it is a great way to see how our life coulg shift depending on what goals we set in our life
6 | 1 | 7_S2_Completed 100% LinkedIn Profile |  | DAY_6 | 0 | Done | 0.5 | https://www.linkedin.com/in/alejo-alegre-bustos-b03395174/
6 | 2 | 18_P3_Cover Letter Template |  | DAY_6 | 0 | Done | 1 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/Alejo%20Alegre%20Bustos%20-%20CL.docx
6 | 3 | 12_S7_Informational Interview 2 |  | DAY_6 | 0 | Done | 0.5 | I interview a persona in a career fair that I attended on Wednesday
|  | Assignment 3 Planned Velocity | 0
7 | 1 | 26_J5_Job Application 2 |  | DAY_7 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/application%20job%202.png
7 | 2 | 10_S5_Resume in Green Zone on VMOCK |  | DAY_7 | 0 | Done | 2 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/vmock-green%20zone.png
7 | 3 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) |  | DAY_7 | 0 | Done | 1 | These chapters focus on targeted, organized outreach instead of sending random applications. You build a LAMP list to prioritize high-value contacts, especially alumni, and craft short, specific emails that clearly state your ask. Tracking responses and next steps in a spreadsheet keeps the process efficient, while batching outreach actions ensures momentum. The key is structure and focus, turning outreach into a repeatable, measurable process.
8 | 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) |  | DAY_8 | 0 | Done | 1 | Execution is about turning planning into results. Focus first on contacts most likely to respond, maintain a consistent cadence of emails and follow-ups, and prepare for calls with clear, actionable questions. Treat the process like an experiment: track what works, refine your approach, and maintain daily consistency. Success comes from disciplined, systematic effort rather than sporadic, high-volume activity.
8 | 2 | 25_J4_Job Application 1 |  | DAY_8 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/application%20job%201.png
8 | 3 | 11_S6_Informational Interview 1 |  | DAY_8 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/informational%20interview%20-%20david%20palmer.pdf
|  | Assignment 4 Planned Velocity | 0
9 | 1 | 21_P6_Projects |  | DAY_9 | 0 | Working | 10 | https://github.com/AlejoAlegreBustos/Machine-learning-projects
9 | 2 | 4_B4_Interviewing: VMOCK |  | DAY_9 | 0 | Done | 1 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/vmock%20interviews.png
9 | 3 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) |  | DAY_9 | 0 | Done | 1.5 | The first four chapters of The 2-Hour Job Search are all about working smarter when job hunting. Instead of sending your résumé everywhere and hoping for luck, Steve Dalton shows a faster way using the LAMP method — List, Alumni, Motivation, and Posting. Basically, you make a list of companies you’d like to work for, see where you’ve got some kind of connection, check which ones actually interest you, and note if they’ve got open roles. Then you rank them, so you know where to start reaching out. It’s a simple system that takes a couple of hours to set up but makes the whole job search way more focused and less stressful.
10 | 1 | 13_S8_Informational Interview 3 |  | DAY_10 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/informational%20interview%203.png
10 | 2 | 16_P1_Photo |  | DAY_10 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/251013_Alejo%20Alegre%20Bustos_002.jpg
10 | 3 | 27_J6_Job Application 3 |  | DAY_10 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/job%20application%203.png
|  | Assignment 5 Planned Velocity | 0
11 | 1 | 19_P4_References |  | DAY_11 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/professional%20reference.pdf
11 | 2 | 40_A2_test 2 |  | DAY_11 | 0 | Done | 0.5 | Placeholder
11 | 3 | 6_S1_Scheduled Silver Meeting with Career Services |  | DAY_11 | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/silver%20certification%20appointment.png
12 | 1 | 24_J3_Company Dossiers |  | DAY_12 | 0 | Done | 1 | In class
12 | 2 | 30_D2_Mental Health & Professional Success |  | DAY_12 | 0 | Done | 1 | In class
12 | 3 | 29_D1_Ethics in Technology |  | DAY_12 | 0 | Done | 1 | In class
|  | Assignment 6 Planned Velocity | 0
13 | 1 | 15_S10_Informational Interview 5 |  | DAY_13 | 0 | Done | 1 | I interviewed someone from Murphy USA, a gas copany, in this case we had the visit of the data and software engineering team, I asked a couple of questions about how is the company implementing math models or ML models in the context of AI
13 | 2 | 22_J1_Networking List |  | DAY_13 | 0 | 0 | 0 | 0
13 | 3 | 41_A3_test 3 |  | DAY_13 | 0 | 0 | 0 | 0
14 | 1 | 42_A4_test 4 |  | DAY_14 | 0 | 0 | 0 | 0
14 | 2 | 39_A1_test1 |  | DAY_14 | 0 | 0 | 0 | 0
14 | 3 | 23_J2_Network Contact List |  | DAY_14 | 0
|  | Assignment 7 Planned Velocity | 0
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points are based on complexity of the assignment, not how long it takes. Start with this assignment as a complexity 5. Compare the next assignment you have on the list more or less complex. Continue rake and stacking the assignment’s complexity. (You can go back and change the complexity).
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points are based on complexity of the assignment, not how long it takes. Start with this assignment as a complexity 5. Compare the next assignment you have on the list more or less complex. Continue rake and stacking the assignment’s complexity. (You can go back and change the complexity).

## A1_Status
|  | Assignment 1: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 1 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 0_PP1_Planning Schedule | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/StudentTrackingAssignments.xlsx
| 2 | 17_P2_Resume | 0 | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/Alejo%20Alegre%20Bustos%20-%20Resume.pdf
| 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love |  | Done | 0.5 | from my perspective, the best to do first is an introspection about our life, to see which jar is full or not in our life(health, work, play, happiness, and love). We can start working from there, after that, it depends on us, our lifestyle, and long-term goals. i think one of the best things we can do is to set priorities in these four sections and build from there.
| Day 2 | Planned |  | Completed? | Actual Hrs
| 1 | 5_B5_Elevator Pitch: 5 Sentences |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/speach-elevetaro.docx
| 2 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass |  | Done | 0.5 | It was a great chapter, it's really great to already have a compas that govern every other aspects in my life. I think the gospel of Jesus-Christ is the best compas we can have in our life, from there we can start thinking about working and what impact we can let it have in our life.
| 3 | 9_S4_Completed 100% Handshake Profile |  | Done | 0.5 | https://byui.joinhandshake.com/profiles/fbc2a9
|  | Total (Velocity) | 0 |  | 3
|  | Average | 0 |  | 0.5
What are you planning on doing?
| Day 3 | Planned |  | See next weeks for status
| 1 | 1_B1_Scheduled Basic Meeting with Career Services
| 2 | 8_S3_Completed 100% BYUI Connect Profile
| 3 | 33_D5_Design Your Life: Chap 3: Good Times Journal
| Day 4 | Planned
| 1 | 2_B2_Create Professional Online Profiles
| 2 | 3_B3_Informational Interview Overview
| 3 | 34_D6_Design Your Life: Chap 4: Mind Map
Obsticales
n/a
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule | Planning my schedule help me to work by pieces a many things, I think it’s a great way to learn in deep a specific subject
| Lesson 2 | 17_P2_Resume | I met with a Professor this week to chek my resume and he pointed many things that were in my resume but with some adjustments make a better impact
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love | It gave me a picture of how to choose the right priorities for the life that I want to live
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences | It help me to briefly introduce my self to a strenger without doubts or time thinking about what I do
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile | I learned how to organize my resume
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | Connect with people: Networking
| Goal 2: | Identify requirements to fill
| Goal 3: | Identify requirements to fill

## A2_Status
|  | Assignment 2: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 3 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 1_B1_Scheduled Basic Meeting with Career Services |  | Done | 0.5 | https://app.joinhandshake.com/stu/appointments/16395626
| 2 | 8_S3_Completed 100% BYUI Connect Profile |  | Done | 1 | https://ces.peoplegrove.com/profile/alejoalegrebustos/
| 3 | 33_D5_Design Your Life: Chap 3: Good Times Journal |  | Done | 1 | This chapter is all about tracking your days to notice what actually gives you energy and makes you feel alive. For a few weeks, you write down what you do, how much energy you had, and how engaged you felt during each activity. The point is to catch the moments when time flies, when you’re fully into something, or when you feel drained. Once you look back at your notes, patterns start to show—things you really enjoy, the settings where you thrive, the kind of work or interactions that light you up. It’s not about what you think you “should” like, but about what your own experience is telling you.
| Day 4 | Planned |  | Completed? | Actual Hrs
| 1 | 2_B2_Create Professional Online Profiles |  | Working
| 2 | 3_B3_Informational Interview Overview |  | Done | 0.5 | https://app.joinhandshake.com/stu/appointments/16395626
| 3 | 34_D6_Design Your Life: Chap 4: Mind Map |  | Done | 1 | After you spot the paterns tought in chapter 3, the next step is to open up possibilities with a mind map. You start with a word or idea from your journal maybe something like “teaching”,“outdoors” or “design.” Put it in the center of a page and let your thoughts branch out. Write down anything that comes to mind, no matter how random. Then branch those ideas again and see where they lead. The goal is to break out of straight line thinking and discover connections or paths you wouldn’t see otherwise.
|  | Total (Velocity) | 0 |  | 4
|  | Average | 0 |  | 0.66667
What are you planning on doing?
| Day 5 | Planned |  | See next weeks for status
| 1 | 20_P5_Elevator Pitch/About
| 2 | 14_S9_Informational Interview 4
| 3 | 35_D7_Design Your Life: Chap 5: Odyssey Plans
| Day 6 | Planned
| 1 | 7_S2_Completed 100% LinkedIn Profile
| 2 | 18_P3_Cover Letter Template
| 3 | 12_S7_Informational Interview 2
Obsticales
n/a
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 1_B1_Scheduled Basic Meeting with Career Services | I think is a great resource to understand your chances to get a job by traditional ways
| Lesson 2 | 8_S3_Completed 100% BYUI Connect Profile | It a great place to know connect with people that is currently working, they are really kind and always willing to give you tips and feedback
| Lesson 3 | 33_D5_Design Your Life: Chap 3: Good Times Journal | great book chapter, I never thought about a good times journar, but it makes sense if you want to really enjoy something that you are going to do for 50 years like work
Planned
| Lesson 4 | 2_B2_Create Professional Online Profiles | still working on this
| Lesson 5 | 3_B3_Informational Interview Overview | I never heard about it before, it is a great way to know what a company offers, the enviroment, what they propose to the employee. Also, to understan what I need to know and to do for some day work there
| Lesson 6 | 34_D6_Design Your Life: Chap 4: Mind Map | the idea to draw your thoughts and ideas in a paper is always good, even if it's not for a work decision, it will help to vizualize your goals
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | Connect with people: Networking
| Goal 2: | Identify requirements to fill
Goal 3:

## A3_Status
|  | Assignment 3: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 5 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 20_P5_Elevator Pitch/About |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/speach-elevetaro.docx
| 2 | 14_S9_Informational Interview 4 |  | Done | 0.5 | I interview a persona in a career fair that I attended on Wednesday
| 3 | 35_D7_Design Your Life: Chap 5: Odyssey Plans |  | Done | 1.5 | I think it is a great way to see how our life coulg shift depending on what goals we set in our life
| Day 6 | Planned |  | Completed? | Actual Hrs
| 1 | 7_S2_Completed 100% LinkedIn Profile |  | Done | 0.5 | https://www.linkedin.com/in/alejo-alegre-bustos-b03395174/
| 2 | 18_P3_Cover Letter Template |  | Done | 1 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/Alejo%20Alegre%20Bustos%20-%20CL.docx
| 3 | 12_S7_Informational Interview 2 |  | Done | 0.5 | I interview a persona in a career fair that I attended on Wednesday
|  | Total (Velocity) | 0 |  | 4.5
|  | Average | 0 |  | 0.75
What are you planning on doing?
| Day 7 | Planned |  | See next weeks for status
| 1 | 26_J5_Job Application 2
| 2 | 10_S5_Resume in Green Zone on VMOCK
| 3 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8)
| Day 8 | Planned
| 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10)
| 2 | 25_J4_Job Application 1
| 3 | 11_S6_Informational Interview 1
Obsticales
short time for informational interviews
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 20_P5_Elevator Pitch/About | Great way to present myself, even to my own family, now I am not loosing time thinking for a good answer for that
| Lesson 2 | 14_S9_Informational Interview 4 | It was a great way to understand where and in what position I want to work, it gave me a better understanding about the diferencies between work positions in companies
| Lesson 3 | 35_D7_Design Your Life: Chap 5: Odyssey Plans
Planned
| Lesson 4 | 7_S2_Completed 100% LinkedIn Profile | It helps me to have something to show to someone when they aske me about my academic experience and work experience
| Lesson 5 | 18_P3_Cover Letter Template | It was great to think how my skills and experiences could be a good fit for the positions I am applying for, it truly is the breach between the application requirements and my resume
| Lesson 6 | 12_S7_Informational Interview 2 | It was a great way to understand where and in what position I want to work, it gave me a better understanding about the diferencies between work positions in companies
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | Connect with people: Networking
| Goal 2: | Identify requirements to fill
Goal 3:

## A4_Status
|  | Assignment 4: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 7 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 26_J5_Job Application 2 |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/application%20job%202.png
| 2 | 10_S5_Resume in Green Zone on VMOCK |  | Done | 2 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/vmock-green%20zone.png
| 3 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) |  | Done | 1 | These chapters focus on targeted, organized outreach instead of sending random applications. You build a LAMP list to prioritize high-value contacts, especially alumni, and craft short, specific emails that clearly state your ask. Tracking responses and next steps in a spreadsheet keeps the process efficient, while batching outreach actions ensures momentum. The key is structure and focus, turning outreach into a repeatable, measurable process.
| Day 8 | Planned |  | Completed? | Actual Hrs
| 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) |  | Done | 1 | Execution is about turning planning into results. Focus first on contacts most likely to respond, maintain a consistent cadence of emails and follow-ups, and prepare for calls with clear, actionable questions. Treat the process like an experiment: track what works, refine your approach, and maintain daily consistency. Success comes from disciplined, systematic effort rather than sporadic, high-volume activity.
| 2 | 25_J4_Job Application 1 |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/application%20job%201.png
| 3 | 11_S6_Informational Interview 1 |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/informational%20interview%20-%20david%20palmer.pdf
|  | Total (Velocity) | 0 |  | 5.5
|  | Average | 0 |  | 0.91667
What are you planning on doing?
| Day 9 | Planned |  | See next weeks for status
| 1 | 21_P6_Projects
| 2 | 4_B4_Interviewing: VMOCK
| 3 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4)
| Day 10 | Planned
| 1 | 13_S8_Informational Interview 3
| 2 | 16_P1_Photo
| 3 | 27_J6_Job Application 3
Obsticales
n/a
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 26_J5_Job Application 2 | I targeted this job for the great experience they offerd, specially with my degree, I have many projects that are directly related with what they are looking for
| Lesson 2 | 10_S5_Resume in Green Zone on VMOCK | Great way to know if you are in the right path or, at least, know that you getting close to it
| Lesson 3 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) | I thing it is a big deal to target companies and positions to have a clear focus of action if not our efforts are just going to be random shoots
Planned
| Lesson 4 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) | There is a great process called data exploration in Data Science, I think that's what these chapters are suggesting us to do, to understand where and when people is most likely to answer and email from a stranger
| Lesson 5 | 25_J4_Job Application 1 | I targeted this job for the great experience they offerd, specially with my degree
| Lesson 6 | 11_S6_Informational Interview 1 | best way to know where you want to work, knowing about benefits, work enviroment and so on, it's a great help before wasting time in a place where you do not belong
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | Connect with people: Networking
| Goal 2: | Identify requirements to fill
| Goal 3: | get an interview

## A5_Status
|  | Assignment 5: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 9 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 21_P6_Projects |  | Working | 10 | https://github.com/AlejoAlegreBustos/Machine-learning-projects
| 2 | 4_B4_Interviewing: VMOCK |  | Done | 1 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/vmock%20interviews.png
| 3 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) |  | Done | 1.5 | The first four chapters of The 2-Hour Job Search are all about working smarter when job hunting. Instead of sending your résumé everywhere and hoping for luck, Steve Dalton shows a faster way using the LAMP method — List, Alumni, Motivation, and Posting. Basically, you make a list of companies you’d like to work for, see where you’ve got some kind of connection, check which ones actually interest you, and note if they’ve got open roles. Then you rank them, so you know where to start reaching out. It’s a simple system that takes a couple of hours to set up but makes the whole job search way more focused and less stressful.
| Day 10 | Planned |  | Completed? | Actual Hrs
| 1 | 13_S8_Informational Interview 3 |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/informational%20interview%203.png
| 2 | 16_P1_Photo |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/251013_Alejo%20Alegre%20Bustos_002.jpg
| 3 | 27_J6_Job Application 3 |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/job%20application%203.png
|  | Total (Velocity) | 0 |  | 14
|  | Average | 0 |  | 2.3333
What are you planning on doing?
| Day 11 | Planned |  | See next weeks for status
| 1 | 19_P4_References
| 2 | 40_A2_test 2
| 3 | 6_S1_Scheduled Silver Meeting with Career Services
| Day 12 | Planned
| 1 | 24_J3_Company Dossiers
| 2 | 30_D2_Mental Health & Professional Success
| 3 | 29_D1_Ethics in Technology
Obsticales
n/a
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 21_P6_Projects | great wat to practice coding, also, it is a excellente way to lear before hand in which branch of data science I would like to work
| Lesson 2 | 4_B4_Interviewing: VMOCK | great way to practice and lose the fear or insecurity that you feel before the interview
| Lesson 3 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) | The first four chapters of The 2-Hour Job Search are all about working smarter when job hunting. Instead of sending your résumé everywhere and hoping for luck, Steve Dalton shows a faster way using the LAMP method — List, Alumni, Motivation, and Posting. Basically, you make a list of companies you’d like to work for, see where you’ve got some kind of connection, check which ones actually interest you, and note if they’ve got open roles. Then you rank them, so you know where to start reaching out. It’s a simple system that takes a couple of hours to set up but makes the whole job search way more focused and less stressful.
Planned
| Lesson 4 | 13_S8_Informational Interview 3 | this time I learn what that informational interviews are great way to know what life style you can have in certain companies
| Lesson 5 | 16_P1_Photo
| Lesson 6 | 27_J6_Job Application 3
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | Connect with people: Networking
| Goal 2: | Identify requirements to fill
| Goal 3: | get an interview

## A6_Status
|  | Assignment 6: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 11 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 19_P4_References |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/professional%20reference.pdf
| 2 | 40_A2_test 2 |  | Done | 0.5 | Placeholder
| 3 | 6_S1_Scheduled Silver Meeting with Career Services |  | Done | 0.5 | https://github.com/AlejoAlegreBustos/Machine-learning-projects/blob/main/CSE%20300/silver%20certification%20appointment.png
| Day 12 | Planned |  | Completed? | Actual Hrs
| 1 | 24_J3_Company Dossiers |  | Done | 1 | In class
| 2 | 30_D2_Mental Health & Professional Success |  | Done | 1 | In class
| 3 | 29_D1_Ethics in Technology |  | Done | 1 | In class
|  | Total (Velocity) | 0 |  | 4.5
|  | Average | 0 |  | 0.75
What are you planning on doing?
| Day 13 | Planned |  | See next weeks for status
| 1 | 15_S10_Informational Interview 5
| 2 | 22_J1_Networking List
| 3 | 41_A3_test 3
| Day 14 | Planned
| 1 | 42_A4_test 4
| 2 | 39_A1_test1
| 3 | 23_J2_Network Contact List
Obsticales
na
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 19_P4_References | great way to keep your resources and networking organize, sometimes your peers talk mor about you than yourself
| Lesson 2 | 40_A2_test 2 | placeholer
| Lesson 3 | 6_S1_Scheduled Silver Meeting with Career Services | I scheduled this appointment for next Monday
Planned
| Lesson 4 | 24_J3_Company Dossiers | great way to know before hand where you are getting into, sometimes you thing "I am going to get the first thing that appears but I could end in a really diferent place than what you planned
| Lesson 5 | 30_D2_Mental Health & Professional Success | really important, mental health is equal or more important than studies or work, if you are not mentaly health you cannot study or work
| Lesson 6 | 29_D1_Ethics in Technology | also, really important,ethics in tech make the difference between help someone and harm someone
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | Connect with people: Networking
| Goal 2: | Identify requirements to fill
| Goal 3: | get an interview

## A7_Status
|  | Assignment 7: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 13 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 15_S10_Informational Interview 5 |  | Done | 1 | I interviewed someone from Murphy USA, a gas copany, in this case we had the visit of the data and software engineering team, I asked a couple of questions about how is the company implementing math models or ML models in the context of AI
| 2 | 22_J1_Networking List
| 3 | 41_A3_test 3
| Day 14 | Planned |  | Completed? | Actual Hrs
| 1 | 42_A4_test 4
| 2 | 39_A1_test1
| 3 | 23_J2_Network Contact List
|  | Total (Velocity) | 0 |  | 1
|  | Average | 0 |  | 0.16667
What are you planning on doing?
| Day 15+ | Planned
| 1 | Work on your goals
| 2 | Work on your odyssy plan
| 3 | Find an Internship
| 1 | Plan for Graduate school
| 2 | Find a full time job
3
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3: