## Status
Class Status
Instructions: | For your first assignment you will need to fill out A0_Plan Each week you will fill out the corresponding Ax_Status tab along with your Team Status. Note the gray fields are the field you need to change. All other fields are formulas that will populate back to this page's status. Submit a copy of this file, updated each week.
| Tasking | Percent Complete | Totals |  | Milestones | Done
| Planned/Scheduled | 97.44% | 0 |  | Basic Certification | 60%
| Story Points Assigned | 0% | 0 |  | Portfolio | 100%
| Completed Tasks | 61.54% | 0 |  | Silver Certification | 60%
[5 empty] | Job Search | 100%
[5 empty] | Professional Development | 10%
| Personal | Velocity | Hrs/Task | Avg Hrs/Task | Team Member | 1 | 2 | 3 | 4 | 5
| Week 01 | 0 | 3 | 0.5 | Week 01 | 0 | 0 | 0 | 0 | 0
| Week 02 | 0 | 2 | 0.33333 | Week 02 | 0 | 0 | 0 | 0 | 0
| Week 03 | 0 | 0.5 | 0.083333 | Week 03 | 0 | 0 | 0 | 0 | 0
| Week 04 | 0 | 0.5 | 0.083333 | Week 04 | 0 | 0 | 0 | 0 | 0
| Week 05 | 0 | 0 | 0 | Week 05 | 0 | 0 | 0 | 0 | 0
| Week 06 | 0 | 0 | 0 | Week 06 | 0 | 0 | 0 | 0 | 0
| Week 07 | 0 | 0 | 0 | Week 07 | 0 | 0 | 0 | 0 | 0

## Team Status
Team member tasking
Completed Tasks
| Day |  | Team member 1 | Team Member 2 | Team Member 3 | Team Member 4
Assignment 1
| 1 | 1
| 1 | 2
| 1 | 3
| 2 | 1
| 2 | 2
| 2 | 3
Velocity
Assignment 2
| 3 | 1
| 3 | 2
| 3 | 3
| 4 | 1
| 4 | 2
| 4 | 3
Velocity
Assignment 3
| 5 | 1
| 5 | 2
| 5 | 3
| 6 | 1
| 6 | 2
| 6 | 3
Velocity
Assignment 4
| 7 | 1
| 7 | 2
| 7 | 3
| 8 | 1
| 8 | 2
| 8 | 3
Velocity
Assignment 5
| 9 | 1
| 9 | 2
| 9 | 3
| 10 | 1
| 10 | 2
| 10 | 3
Velocity
Assignment 6
| 11 | 1
| 11 | 2
| 11 | 3
| 12 | 1
| 12 | 2
| 12 | 3
Velocity
Assignment 7
| 13 | 1
| 13 | 2
| 13 | 3
| 14 | 1
| 14 | 2
| 14 | 3
Velocity

## Backlog
BackLog
Count | Ref | Issues | Hidden Colum - create a orginal menu list | Hidden Column - menu list that removes items as selected |  | Hidden status
[5 empty] | 97.44% | 61.54%
0 | PP1 | Planning Schedule | 0_PP1_Planning Schedule |  | 1 | 1 | Completed
0 | B0 | Basic Certification |  |  |  |  | 60%
1 | B1 | Scheduled Basic Meeting with Career Services | 1_B1_Scheduled Basic Meeting with Career Services |  | 1 | 1
2 | B2 | Create Professional Online Profiles | 2_B2_Create Professional Online Profiles |  | 1 | 1
3 | B3 | Informational Interview Overview | 3_B3_Informational Interview Overview |  | 1 | 1
4 | B4 | Interviewing: VMOCK | 4_B4_Interviewing: VMOCK |  | 1
5 | B5 | Elevator Pitch: 5 Sentences | 5_B5_Elevator Pitch: 5 Sentences |  | 1
0 | S0 | Silver Certification |  |  |  |  | 60%
6 | S1 | Scheduled Silver Meeting with Career Services | 6_S1_Scheduled Silver Meeting with Career Services |  | 1
7 | S2 | Completed 100% LinkedIn Profile | 7_S2_Completed 100% LinkedIn Profile |  | 1
8 | S3 | Completed 100% BYUI Connect Profile | 8_S3_Completed 100% BYUI Connect Profile |  | 1
9 | S4 | Completed 100% Handshake Profile | 9_S4_Completed 100% Handshake Profile |  | 1
10 | S5 | Resume in Green Zone on VMOCK | 10_S5_Resume in Green Zone on VMOCK |  | 1 | 1
11 | S6 | Informational Interview 1 | 11_S6_Informational Interview 1 |  | 1 | 1
12 | S7 | Informational Interview 2 | 12_S7_Informational Interview 2 |  | 1 | 1
13 | S8 | Informational Interview 3 | 13_S8_Informational Interview 3 |  | 1 | 1
14 | S9 | Informational Interview 4 | 14_S9_Informational Interview 4 |  | 1 | 1
15 | S10 | Informational Interview 5 | 15_S10_Informational Interview 5 |  | 1 | 1
0 | P0 | Portfolio Review |  |  |  |  | 100%
16 | P1 | Photo | 16_P1_Photo |  | 1 | 1
17 | P2 | Resume | 17_P2_Resume |  | 1 | 1
18 | P3 | Cover Letter Template | 18_P3_Cover Letter Template |  | 1 | 1
19 | P4 | References | 19_P4_References |  | 1 | 1
20 | P5 | Elevator Pitch/About | 20_P5_Elevator Pitch/About |  | 1 | 1
21 | P6 | Projects | 21_P6_Projects |  | 1 | 1
0 | J0 | Job Search |  |  |  |  | 100%
22 | J1 | Networking List | 22_J1_Networking List |  | 1 | 1
23 | J2 | Network Contact List | 23_J2_Network Contact List |  | 1 | 1
24 | J3 | Company Dossiers | 24_J3_Company Dossiers |  | 1 | 1
25 | J4 | Job Application 1 | 25_J4_Job Application 1 |  | 1 | 1
26 | J5 | Job Application 2 | 26_J5_Job Application 2 |  | 1 | 1
27 | J6 | Job Application 3 | 27_J6_Job Application 3 |  | 1 | 1
28 | J7 | Job Interviewing | 28_J7_Job Interviewing | 28_J7_Job Interviewing |  | 1
0 | D0 | Professional Development |  |  |  |  | 10%
29 | D1 | Ethics in Technology | 29_D1_Ethics in Technology |  | 1 | 1
30 | D2 | Mental Health & Professional Success | 30_D2_Mental Health & Professional Success |  | 1
31 | D3 | Design Your Life: Chap 1: Health, Work, Play, & Love | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love |  | 1
32 | D4 | Design Your Life: Chap 2: Work/Life view/compass | 32_D4_Design Your Life: Chap 2: Work/Life view/compass |  | 1
33 | D5 | Design Your Life: Chap 3: Good Times Journal | 33_D5_Design Your Life: Chap 3: Good Times Journal |  | 1
34 | D6 | Design Your Life: Chap 4: Mind Map | 34_D6_Design Your Life: Chap 4: Mind Map |  | 1
35 | D7 | Design Your Life: Chap 5: Odyssey Plans | 35_D7_Design Your Life: Chap 5: Odyssey Plans |  | 1
36 | D8 | The 2-Hour Job Search: Prioritization (Chap 1-4) | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) |  | 1
37 | D9 | The 2-Hour Job Search: Outreach (Chap 5-8) | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) |  | 1
38 | D10 | The 2-Hour Job Search: Execution (Chap 9-10) | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) |  | 1
0 | A0 | Additional Tasks
39 | A1 | test1 | 39_A1_test1
40 | A2 | test 2 | 40_A2_test 2
41 | A3 | test 3 | 41_A3_test 3
42 | A4 | test 4 | 42_A4_test 4

## A0_Plan
|  |  |  | Hidden | Hidden | Hidden | Hidden | Hidden
Assign 0: Planning Schedule | [9 empty] | Story Points Chart
Instructions: | [9 empty] | Complexity | Complexity Description | CS Example Task | Class Example
1 | Read over each of the assignments in the Backlog (found in iLearn course) In the Planning Assignment column, select which task you plan on completing for each day of the semester. | [7 empty] | 1 | 1 Point | Very simple, minimal effort, well understood | Change a button's color in a web app | - Upload a photo for portfolio - Schedule a meeting with Career Services
2 | Examine the Story Point chart to the right. Mouse over and Read the comment in the Story Point column's title (below). | [7 empty] | 2 | 2 Points | Simple task, few moving parts | Add a new field to a database and update UI | - Create Networking List - Write 5-sentence Elevator Pitch
3 | Assign story points to each of the assignments, based on the complexity of the task. | [7 empty] | 3 | 3 Points | Moderate complexity; some research or testing needed | Implement login with form validation | - Complete LinkedIn or Handshake profile - Read and reflect on “Design Your Life: Chap 1–2”
4 | Verify that the Planned Velocity Chart has a even variance and trend. | [7 empty] | 5 | 5 Points | Complex; multiple steps or edge cases | Integrate third-party API (e.g., payment gateway) | - Write a resume or cover letter template - Conduct Informational Interview 1–2
[9 empty] | 8 | 8 Points | Very complex; uncertainty, multiple components | Build a basic real-time chat feature | - Resume in Green Zone on VMOCK - Conduct 4–5 Informational Interviews - Projects section for Portfolio
[9 empty] | 13 | 13 Points | Extremely complex or poorly understood | Refactor large legacy module or migrate backend | - Prepare for and perform Job Interviews - Create full Odyssey Plans (Design Your Life: Chap 5) - Apply to 3 jobs with custom materials
[9 empty] | 21 | 21+ Points | Too large – break this down | “Build entire website” — needs decomposition | - "Complete All Silver Certification Requirements" (too broad; break into subtasks)
Day |  | Planned Assignment | Story Points | Scheduled | SP Complete | Completed | Actual Hours | Linke to Artifacts
1 | 1 | 0_PP1_Planning Schedule | 0 | DAY_1 | 0 | Done | 0.5 | Missing
1 | 2 | 17_P2_Resume | 0 | DAY_1 | 0 | Done | 0.5 | 0
1 | 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love |  | DAY_1 | 0 | Done | 0.5 | 0
2 | 1 | 5_B5_Elevator Pitch: 5 Sentences |  | DAY_2 | 0 | Done | 0.5 | 0
2 | 2 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass |  | DAY_2 | 0 | Done | 0.5 | 0
2 | 3 | 9_S4_Completed 100% Handshake Profile |  | DAY_2 | 0 | Done | 0.5 | 0
|  | Assignment 1 Planned Velocity | 0
3 | 1 | 1_B1_Scheduled Basic Meeting with Career Services |  | DAY_3 | 0 | Done | 0.5 | 0
3 | 2 | 8_S3_Completed 100% BYUI Connect Profile |  | DAY_3 | 0 | Done | 1 | 0
3 | 3 | 33_D5_Design Your Life: Chap 3: Good Times Journal |  | DAY_3 | 0 | 0 | 0 | 0
4 | 1 | 2_B2_Create Professional Online Profiles |  | DAY_4 | 0 | 0 | 0 | 0
4 | 2 | 3_B3_Informational Interview Overview |  | DAY_4 | 0 | Done | 0.5 | 0
4 | 3 | 34_D6_Design Your Life: Chap 4: Mind Map |  | DAY_4 | 0 | 0 | 0 | 0
|  | Assignment 2 Planned Velocity | 0
5 | 1 | 20_P5_Elevator Pitch/About |  | DAY_5 | 0 | 0 | 0 | 0
5 | 2 | 4_B4_Interviewing: VMOCK |  | DAY_5 | 0 | 0 | 0 | 0
5 | 3 | 35_D7_Design Your Life: Chap 5: Odyssey Plans |  | DAY_5 | 0 | 0 | 0 | 0
6 | 1 | 7_S2_Completed 100% LinkedIn Profile |  | DAY_6 | 0 | Done | 0.5 | 0
6 | 2 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) |  | DAY_6 | 0 | 0 | 0 | 0
6 | 3 | 16_P1_Photo |  | DAY_6 | 0 | 0 | 0 | 0
|  | Assignment 3 Planned Velocity | 0
7 | 1 | 26_J5_Job Application 2 |  | DAY_7 | 0 | 0 | 0 | 0
7 | 2 | 10_S5_Resume in Green Zone on VMOCK |  | DAY_7 | 0 | Done | 0.5 | 0
7 | 3 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) |  | DAY_7 | 0 | 0 | 0 | 0
8 | 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) |  | DAY_8 | 0 | 0 | 0 | 0
8 | 2 | 25_J4_Job Application 1 |  | DAY_8 | 0 | 0 | 0 | 0
8 | 3 | 11_S6_Informational Interview 1 |  | DAY_8 | 0 | 0 | 0 | 0
|  | Assignment 4 Planned Velocity | 0
9 | 1 | 22_J1_Networking List |  | DAY_9 | 0 | 0 | 0 | 0
9 | 2 | 39_A1_test1 |  | DAY_9 | 0 | 0 | 0 | 0
9 | 3 | 18_P3_Cover Letter Template |  | DAY_9 | 0 | 0 | 0 | 0
10 | 1 | 29_D1_Ethics in Technology |  | DAY_10 | 0 | 0 | 0 | 0
10 | 2 | 12_S7_Informational Interview 2 |  | DAY_10 | 0 | 0 | 0 | 0
10 | 3 | 19_P4_References |  | DAY_10 | 0 | 0 | 0 | 0
|  | Assignment 5 Planned Velocity | 0
11 | 1 | 13_S8_Informational Interview 3 |  | DAY_11 | 0 | 0 | 0 | 0
11 | 2 | 40_A2_test 2 |  | DAY_11 | 0 | 0 | 0 | 0
11 | 3 | 23_J2_Network Contact List |  | DAY_11 | 0 | 0 | 0 | 0
12 | 1 | 14_S9_Informational Interview 4 |  | DAY_12 | 0 | 0 | 0 | 0
12 | 2 | 30_D2_Mental Health & Professional Success |  | DAY_12 | 0 | 0 | 0 | 0
12 | 3 | 27_J6_Job Application 3 |  | DAY_12 | 0 | 0 | 0 | 0
|  | Assignment 6 Planned Velocity | 0
13 | 1 | 15_S10_Informational Interview 5 |  | DAY_13 | 0 | 0 | 0 | 0
13 | 2 | 24_J3_Company Dossiers |  | DAY_13 | 0 | 0 | 0 | 0
13 | 3 | 41_A3_test 3 |  | DAY_13 | 0 | 0 | 0 | 0
14 | 1 | 42_A4_test 4 |  | DAY_14 | 0 | 0 | 0 | 0
14 | 2 | 21_P6_Projects |  | DAY_14 | 0 | 0 | 0 | 0
14 | 3 | 6_S1_Scheduled Silver Meeting with Career Services |  | DAY_14 | 0
|  | Assignment 7 Planned Velocity | 0
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points are based on complexity of the assignment, not how long it takes. Start with this assignment as a complexity 5. Compare the next assignment you have on the list more or less complex. Continue rake and stacking the assignment’s complexity. (You can go back and change the complexity).
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points are based on complexity of the assignment, not how long it takes. Start with this assignment as a complexity 5. Compare the next assignment you have on the list more or less complex. Continue rake and stacking the assignment’s complexity. (You can go back and change the complexity).

## A1_Status
|  | Assignment 1: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 1 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 0_PP1_Planning Schedule | 0 | Done | 0.5
| 2 | 17_P2_Resume | 0 | Done | 0.5
| 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love |  | Done | 0.5
| Day 2 | Planned |  | Completed? | Actual Hrs
| 1 | 5_B5_Elevator Pitch: 5 Sentences |  | Done | 0.5
| 2 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass |  | Done | 0.5
| 3 | 9_S4_Completed 100% Handshake Profile |  | Done | 0.5
|  | Total (Velocity) | 0 |  | 3
|  | Average | 0 |  | 0.5
What are you planning on doing?
| Day 3 | Planned |  | See next weeks for status
| 1 | 1_B1_Scheduled Basic Meeting with Career Services
| 2 | 8_S3_Completed 100% BYUI Connect Profile
| 3 | 33_D5_Design Your Life: Chap 3: Good Times Journal
| Day 4 | Planned
| 1 | 2_B2_Create Professional Online Profiles
| 2 | 3_B3_Informational Interview Overview
| 3 | 34_D6_Design Your Life: Chap 4: Mind Map
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A2_Status
|  | Assignment 2: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 3 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 1_B1_Scheduled Basic Meeting with Career Services |  | Done | 0.5
| 2 | 8_S3_Completed 100% BYUI Connect Profile |  | Done | 1
| 3 | 33_D5_Design Your Life: Chap 3: Good Times Journal
| Day 4 | Planned |  | Completed? | Actual Hrs
| 1 | 2_B2_Create Professional Online Profiles
| 2 | 3_B3_Informational Interview Overview |  | Done | 0.5
| 3 | 34_D6_Design Your Life: Chap 4: Mind Map
|  | Total (Velocity) | 0 |  | 2
|  | Average | 0 |  | 0.33333
What are you planning on doing?
| Day 5 | Planned |  | See next weeks for status
| 1 | 20_P5_Elevator Pitch/About
| 2 | 4_B4_Interviewing: VMOCK
| 3 | 35_D7_Design Your Life: Chap 5: Odyssey Plans
| Day 6 | Planned
| 1 | 7_S2_Completed 100% LinkedIn Profile
| 2 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4)
| 3 | 16_P1_Photo
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A3_Status
|  | Assignment 3: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 5 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 20_P5_Elevator Pitch/About
| 2 | 4_B4_Interviewing: VMOCK
| 3 | 35_D7_Design Your Life: Chap 5: Odyssey Plans
| Day 6 | Planned |  | Completed? | Actual Hrs
| 1 | 7_S2_Completed 100% LinkedIn Profile |  | Done | 0.5
| 2 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4)
| 3 | 16_P1_Photo
|  | Total (Velocity) | 0 |  | 0.5
|  | Average | 0 |  | 0.083333
What are you planning on doing?
| Day 7 | Planned |  | See next weeks for status
| 1 | 26_J5_Job Application 2
| 2 | 10_S5_Resume in Green Zone on VMOCK
| 3 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8)
| Day 8 | Planned
| 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10)
| 2 | 25_J4_Job Application 1
| 3 | 11_S6_Informational Interview 1
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A4_Status
|  | Assignment 4: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 7 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 26_J5_Job Application 2
| 2 | 10_S5_Resume in Green Zone on VMOCK |  | Done | 0.5
| 3 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8)
| Day 8 | Planned |  | Completed? | Actual Hrs
| 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10)
| 2 | 25_J4_Job Application 1
| 3 | 11_S6_Informational Interview 1
|  | Total (Velocity) | 0 |  | 0.5
|  | Average | 0 |  | 0.083333
What are you planning on doing?
| Day 9 | Planned |  | See next weeks for status
| 1 | 22_J1_Networking List
| 2 | 39_A1_test1
| 3 | 18_P3_Cover Letter Template
| Day 10 | Planned
| 1 | 29_D1_Ethics in Technology
| 2 | 12_S7_Informational Interview 2
| 3 | 19_P4_References
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A5_Status
|  | Assignment 5: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 9 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 22_J1_Networking List
| 2 | 39_A1_test1
| 3 | 18_P3_Cover Letter Template
| Day 10 | Planned |  | Completed? | Actual Hrs
| 1 | 29_D1_Ethics in Technology
| 2 | 12_S7_Informational Interview 2
| 3 | 19_P4_References
|  | Total (Velocity) | 0 |  | 0
|  | Average | 0 |  | 0
What are you planning on doing?
| Day 11 | Planned |  | See next weeks for status
| 1 | 13_S8_Informational Interview 3
| 2 | 40_A2_test 2
| 3 | 23_J2_Network Contact List
| Day 12 | Planned
| 1 | 14_S9_Informational Interview 4
| 2 | 30_D2_Mental Health & Professional Success
| 3 | 27_J6_Job Application 3
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A6_Status
|  | Assignment 6: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 11 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 13_S8_Informational Interview 3
| 2 | 40_A2_test 2
| 3 | 23_J2_Network Contact List
| Day 12 | Planned |  | Completed? | Actual Hrs
| 1 | 14_S9_Informational Interview 4
| 2 | 30_D2_Mental Health & Professional Success
| 3 | 27_J6_Job Application 3
|  | Total (Velocity) | 0 |  | 0
|  | Average | 0 |  | 0
What are you planning on doing?
| Day 13 | Planned |  | See next weeks for status
| 1 | 15_S10_Informational Interview 5
| 2 | 24_J3_Company Dossiers
| 3 | 41_A3_test 3
| Day 14 | Planned
| 1 | 42_A4_test 4
| 2 | 21_P6_Projects
| 3 | 6_S1_Scheduled Silver Meeting with Career Services
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A7_Status
|  | Assignment 7: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 13 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 15_S10_Informational Interview 5
| 2 | 24_J3_Company Dossiers
| 3 | 41_A3_test 3
| Day 14 | Planned |  | Completed? | Actual Hrs
| 1 | 42_A4_test 4
| 2 | 21_P6_Projects
| 3 | 6_S1_Scheduled Silver Meeting with Career Services
|  | Total (Velocity) | 0 |  | 0
|  | Average | 0 |  | 0
What are you planning on doing?
| Day 15+ | Planned
| 1 | Work on your goals
| 2 | Work on your odyssy plan
| 3 | Find an Internship
| 1 | Plan for Graduate school
| 2 | Find a full time job
3
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 17_P2_Resume
| Lesson 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
Planned
| Lesson 4 | 5_B5_Elevator Pitch: 5 Sentences
| Lesson 5 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| Lesson 6 | 9_S4_Completed 100% Handshake Profile
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3: